## WBSData
WBS | Name | 输入 | 输出
1 | 软件工程系列渔乐生活APP需求工程计划
1.1 | 项目准备
1.1.1 | 项目任务书下达 | 项目提出 | 项目确认
1.1.2 | logo设计 | 素材 | 渔乐生活logo
1.1.3 | 小组会议 | 学习笔记 | 会议记录
1.1.4 | 软件资源配置 | 安装 | 软件资源
1.1.5 | UML学习
1.1.6 | 与杨枨老师确认项目大致内容 | 谈话记录 | 录音资料
1.2 | 项目启动
1.2.1 | 可行性分析
1.2.1.1 | 小组会议 | 学习笔记 | 会议记录
1.2.1.2 | 可行性分析文档完成 | 初步可行性分析文档，可行性文档中的图表 | 可行性分析文档
1.3 | 项目计划
1.3.1 | 需求工程阶段-初步
1.3.1.1 | 小组会议 | 学习笔记 | 会议记录
1.3.1.2 | 需求工程起草 | 会议记录 | 需求工程起草文档
1.3.1.3 | 甘特图 | 会议记录 | 甘特图
1.3.1.4 | OBS | 甘特图 | OBS
1.3.1.5 | WBS | 甘特图 | WBS
1.3.1.6 | 项目章程
1.3.1.7 | 项目计划起草 | OBS、WBS | 项目计划原型
1.3.2 | 需求工程阶段-修订
1.3.2.1 | 需求工程起草文档修订 | 需求工程起草文档 | 需求工程文档
1.3.2.2 | 项目计划修订 | 项目计划原型 | 项目计划
1.3.3 | 需求获取
1.3.3.1 | 定义愿景和范围 | 项目计划 | 定义结果
1.3.3.2 | 确定需求开发过程 | 定义结果 | 开发过程
1.3.3.3 | 用户群分类 | 软件使用目标 | 分类结果
1.3.3.4 | 小组会议 | 学习笔记 | 会议记录
1.3.3.5 | 选择产品代表 | 会议记录 | 选择结果
1.3.3.6 | 建立核心队伍 | 会议记录 | 核心队伍
1.3.3.7 | 与杨枨老师进行需求访谈 | 会议记录 | 访谈记录
1.3.3.8 | 确定使用实例 | 会议记录 | 使用实例
1.3.3.9 | 小组会议 | 学习笔记 | 会议记录
1.3.3.10 | 分析用户工作流程 | 用户工作流程 | 分析结果
1.3.3.11 | 确定质量属性 | 确定质量属性 | 确定结果
1.3.3.12 | 检查问题报告 | 检查问题报告 | 检查结果
1.3.3.13 | 需求重用 | 用户需求 | 确认结果
1.3.3.14 | 小组会议 | 学习笔记 | 会议记录
1.3.3.15 | 与杨枨老师进行需求确认 | 会议记录 | 与杨枨老师确认结果
1.3.3.16 | 小组会议 | 与杨枨老师确认结果 | 会议记录
1.3.3.17 | 需求整理
1.3.4 | 需求分析
1.3.4.1 | 绘制关联图 | 需求内容 | 关联图
1.3.4.2 | 创建开发原型 | 关联图 | 需求原型
1.3.4.3 | 分析可行性 | 需求原型 | 可行性分析文档
1.3.4.4 | 确定需求优先级 | 可行性分析文档 | 需求优先级结果
1.3.4.5 | 为需求建立模型 | 需求优先级结果 | 需求模型
1.3.4.6 | 小组会议 | 需求模型 | 会议记录
1.3.4.7 | 与杨枨老师进行需求访谈 | 会议记录 | 访谈记录
1.3.4.8 | UML学习
1.3.4.9 | 编写数据字典 | 系统内容 | 数据字典
1.3.4.10 | 小组会议 | 数据字典 | 会议记录
1.3.4.11 | UML复习
1.3.5 | 需求规格说明
1.3.5.1 | 小组会议 | 需求分析文档 | 会议记录
1.3.5.2 | 与杨枨老师进行访谈 | 会议记录 | 访谈记录
1.3.5.3 | 采用软件需求规格说明模板 | 访谈记录 | 模板采用结果
1.3.5.4 | 小组会议 | 模板采用结果 | 会议记录
1.3.5.5 | 指明需求来源 | 需求记录 | 明确来源
1.3.5.6 | 钓鱼用户访谈 | 明确来源 | 访谈记录
1.3.5.7 | 小组会议 | 访谈记录 | 会议记录
1.3.5.8 | 为每一项需求注上记号 | 会议记录 | 标识需求
1.3.5.9 | UML学习
1.3.5.10 | 记录业务规范 | 项目需求 | 业务规范
1.3.5.11 | UML复习
1.3.5.12 | 小组会议 | 业务规范 | 会议记录
1.3.5.13 | 整理成需求规格说明书 | 会议记录 | 需求规格说明书
1.3.5.14 | 与杨枨老师进行交流 | 需求规格说明书 | 交流记录
1.3.5.15 | 小组会议 | 交流记录 | 会议记录
1.3.6 | 管理员访谈
1.3.7 | 召开应用供需开发联系会议
1.4 | 项目控制
1.4.1 | 需求规格审核
1.4.1.1 | 审查需求文档 | 需求规格说明书 | 审查结果
1.4.1.2 | 小组会议 | 审查结果 | 会议记录
1.4.1.3 | 编写需求文档 | 会议记录 | 需求文档
1.4.1.4 | 编写用户手册 | 需求文档 | 用户手册
1.4.1.5 | 确定合格的标准 | 用户手册 | 合格标准
1.4.1.6 | 管理员访谈 | 合格标准 | 访谈记录
1.4.1.7 | 小组会议 | 访谈记录 | 会议记录
1.4.1.8 | 与杨枨老师进行交流 | 会议记录 | 交流记录
1.4.2 | 需求管理
1.4.2.1 | 小组会议 | 交流记录 | 会议记录
1.4.2.2 | 确定变更控制过程 | 会议记录 | 变更控制过程
1.4.2.3 | 建立变更控制委员会 | 变更控制过程 | 变更控制委员会
1.4.2.4 | 进行变更影响分析 | 变更控制委员会 | 变更影响分析
1.4.2.5 | 跟踪每一项变更 | 变更影响分析 | 跟踪状态记录
1.4.2.6 | 编写需求文档的基准版本和控制版本 | 跟踪状态记录 | 需求文档基准版本和控制版本
1.4.2.7 | 维护变更历史纪录 | 需求文档基准版本和控制版本 | 维护结果
1.4.2.8 | 小组会议 | 维护结果 | 会议记录
1.4.2.9 | 跟踪需求状态 | 会议记录 | 跟踪状态记录
1.4.2.10 | 衡量需求稳定性 | 跟踪状态记录 | 需求稳定性记录
1.4.2.11 | 使用需求管理工具 | 需求稳定性记录 | 存储需求
1.5 | 项目收尾
1.5.1 | 文档整理 | 需求规格说明书 | 项目文档
1.5.2 | 制作PPT | 需求稳定性记录 | ppt
1.5.3 | 小组会议 | ppt | 会议记录
1.5.4 | 答辩

## TempData (hidden)
Work- | Baseline Work- | Actual Work- | Work Variance- | Remaining Work- | Cost- | Baseline Cost- | Actual Cost- | Fixed Cost- | Cost Variance- | Remaining Cost- | BCWP- | BCWS- | SV- | Name+ | Notes+ | WBS+ | Constraint Type+ | Constraint Date= | Critical+ | Delay- | Free Slack- | Total Slack- | ID- | Milestone+ | Priority+ | Subproject+ | Baseline Duration- | Actual Duration- | Duration- | Duration Variance- | Remaining Duration- | Percent Complete-[% Complete] | Percent Work Complete-[% Work Complete] | Start= | Finish= | Early Start= | Early Finish= | Late Start= | Late Finish= | Actual Start= | Actual Finish= | Baseline Start= | Baseline Finish= | Start Variance- | Finish Variance- | Predecessors+ | Successors+ | Resource Names+ | Resource Initials+ | Text1+[输入] | Start1= | Finish1= | Text2+[输出] | Start2= | Finish2= | Text3+ | Start3= | Finish3= | Text4+ | Start4= | Finish4= | Text5+ | Start5= | Finish5= | Text6+ | Text7+ | Text8+ | Text9+ | Text10+ | Marked+ | Flag1+ | Flag2+ | Flag3+ | Flag4+ | Flag5+ | Flag6+ | Flag7+ | Flag8+ | Flag9+ | Flag10+ | Rollup+ | CV- | Project+ | Outline Level- | Unique ID- | Number1- | Number2- | Number3- | Number4- | Number5- | Summary+ | Created= | Unique ID Predecessors+ | Unique ID Successors+ | Objects- | Linked Fields+ | Resume= | Stop= | Resume No Earlier Than= | Outline Number+ | Duration1- | Duration2- | Duration3- | Cost1- | Cost2- | Cost3- | Hide Bar+ | Confirmed+ | Update Needed+ | Contact+ | Resource Group+ | ACWP- | Type+ | Recurring+ | Effort Driven+ | Overtime Work- | Actual Overtime Work- | Remaining Overtime Work- | Regular Work- | Overtime Cost- | Actual Overtime Cost- | Remaining Overtime Cost- | Fixed Cost Accrual+ | Hyperlink+ | Hyperlink Address+ | Hyperlink SubAddress+ | Hyperlink Href+ | Assignment+ | Overallocated+ | External Task+ | Subproject Read Only+ | Response Pending+ | TeamStatus Pending+ | Leveling Can Split+ | Level Assignments+ | Work Contour+ | Cost4- | Cost5- | Cost6- | Cost7- | Cost8- | Cost9- | Cost10- | Date1= | Date2= | Date3= | Date4= | Date5= | Date6= | Date7= | Date8= | Date9= | Date10= | Duration4- | Duration5- | Duration6- | Duration7- | Duration8- | Duration9- | Duration10- | Start6= | Finish6= | Start7= | Finish7= | Start8= | Finish8= | Start9= | Finish9= | Start10= | Finish10= | Flag11+ | Flag12+ | Flag13+ | Flag14+ | Flag15+ | Flag16+ | Flag17+ | Flag18+ | Flag19+ | Flag20+ | Number6- | Number7- | Number8- | Number9- | Number10- | Number11- | Number12- | Number13- | Number14- | Number15- | Number16- | Number17- | Number18- | Number19- | Number20- | Text11+ | Text12+ | Text13+ | Text14+ | Text15+ | Text16+ | Text17+ | Text18+ | Text19+ | Text20+ | Text21+ | Text22+ | Text23+ | Text24+ | Text25+ | Text26+ | Text27+ | Text28+ | Text29+ | Text30+ | Assignment Delay- | Assignment Units- | Cost Rate Table+ | Preleveled Start= | Preleveled Finish= | WBS Predecessors+ | WBS Successors+ | Deadline= | Outline Code1+ | Outline Code2+ | Outline Code3+ | Outline Code4+ | Outline Code5+ | Outline Code6+ | Outline Code7+ | Outline Code8+ | Outline Code9+ | Outline Code10+ | Status+ | Physical Percent Complete-[Physical % Complete] | SVPercent- | CVPercent- | Calendar+
1,059.83h | 0h | 0h | 1,059.83h | 1,059.83h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 软件工程系列渔乐生活APP需求工程计划 |  | 1 | 越早越好 |  |  | 0ed | 0d | 0d | 1 | 楍 | 500 |  | 0d | 0d | 82d | 82d | 82d | 0% | 0% | 2018-09-19 08:00 | 2019-01-09 17:00 | 2018-09-19 08:00 | 2019-01-09 17:00 | 2018-09-19 08:00 | 2019-01-09 17:00 |  |  |  |  | 0d | 0d | [24 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 1 | 1 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 19:59 |  |  | 0 | 楍 |  |  |  | 1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 1,059.83h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [15 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
132.8h | 0h | 0h | 132.8h | 132.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目准备 |  | 1.1 | 越早越好 |  |  | 0ed | 0d | 0d | 2 | 楍 | 500 |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2018-09-19 08:00 | 2018-09-24 17:00 | 2018-09-19 08:00 | 2018-09-24 17:00 | 2018-09-19 08:00 | 2018-09-24 17:00 |  |  |  |  | 0d | 0d | [24 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 2 | 59 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 20:04 |  |  | 0 | 楍 |  |  |  | 1.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 132.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A | [15 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
0.8h | 0h | 0h | 0.8h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目任务书下达 |  | 1.1.1 | 越早越好 |  |  | 0ed | 0d | 0d | 3 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-09-19 08:00 | 2018-09-19 08:48 | 2018-09-19 08:00 | 2018-09-19 08:48 | 2018-09-19 08:00 | 2018-09-19 08:48 |  |  |  |  | 0d | 0d |  | 4 | 赵豪杰 | 赵 | 项目提出 |  |  | 项目确认 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 60 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:17 |  | 61 | 0 | 楍 |  |  |  | 1.1.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  |  | 1.1.2 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | logo设计 |  | 1.1.2 | 越早越好 |  |  | 0ed | 0d | 0d | 4 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-09-19 08:48 | 2018-09-20 08:48 | 2018-09-19 08:48 | 2018-09-20 08:48 | 2018-09-19 08:48 | 2018-09-20 08:48 |  |  |  |  | 0d | 0d | 3 | 5 | 苏碧青 | 苏 | 素材 |  |  | 渔乐生活logo | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 61 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:21 | 60 | 62 | 0 | 楍 |  |  |  | 1.1.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.1 | 1.1.3 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.1.3 | 越早越好 |  |  | 0ed | 0d | 0d | 5 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-09-20 08:48 | 2018-09-20 09:36 | 2018-09-20 08:48 | 2018-09-20 09:36 | 2018-09-20 08:48 | 2018-09-20 09:36 |  |  |  |  | 0d | 0d | 4 | 6 | 赵豪杰,张嘉诚,罗培城,苏碧青,郑丞钧 | 赵,张,罗,苏,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 62 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:21 | 61 | 63 | 0 | 楍 |  |  |  | 1.1.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.2 | 1.1.4 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 软件资源配置 |  | 1.1.4 | 越早越好 |  |  | 0ed | 0d | 0d | 6 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-09-20 09:36 | 2018-09-21 09:36 | 2018-09-20 09:36 | 2018-09-21 09:36 | 2018-09-20 09:36 | 2018-09-21 09:36 |  |  |  |  | 0d | 0d | 5 | 7 | 罗培城 | 罗 | 安装 |  |  | 软件资源 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 63 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:22 | 62 | 64 | 0 | 楍 |  |  |  | 1.1.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.3 | 1.1.5 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
72h | 0h | 0h | 72h | 72h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | UML学习 |  | 1.1.5 | 越早越好 |  |  | 0ed | 0d | 0d | 7 | 楍 | 500 |  | 0d | 0d | 1.8d | 1.8d | 1.8d | 0% | 0% | 2018-09-21 09:36 | 2018-09-22 17:00 | 2018-09-21 09:36 | 2018-09-22 17:00 | 2018-09-21 09:36 | 2018-09-24 08:00 |  |  |  |  | 0d | 0d | 6 | 8 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 64 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:38 | 63 | 65 | 0 | 楍 |  |  |  | 1.1.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 72h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.4 | 1.1.6 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师确认项目大致内容 |  | 1.1.6 | 越早越好 |  |  | 0ed | 0d | 0d | 8 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-09-24 08:00 | 2018-09-24 17:00 | 2018-09-24 08:00 | 2018-09-24 17:00 | 2018-09-24 08:00 | 2018-09-25 08:00 |  |  |  |  | 0d | 0d | 7 | 10,11,9 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 谈话记录 |  |  | 录音资料 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 65 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 20:36 | 64 | 14,15,24 | 0 | 楍 |  |  |  | 1.1.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.5 | 1.2.1,1.2.1.1,1.2 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
19.2h | 0h | 0h | 19.2h | 19.2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目启动 |  | 1.2 | 越早越好 |  |  | 0ed | 0d | 0d | 9 | 楍 | 500 |  | 0d | 0d | 3d | 3d | 3d | 0% | 0% | 2018-09-24 08:00 | 2018-09-26 17:00 | 2018-09-24 08:00 | 2018-09-26 17:00 | 2018-09-25 08:00 | 2018-09-26 17:00 |  |  |  |  | 0d | 0d | 8 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 2 | 24 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 21:50 | 65 |  | 0 | 楍 |  |  |  | 1.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 19.2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.6 | [12 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
19.2h | 0h | 0h | 19.2h | 19.2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 可行性分析 |  | 1.2.1 | 越早越好 |  |  | 0ed | 0d | 0d | 10 | 楍 | 500 |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2018-09-25 08:00 | 2018-09-26 17:00 | 2018-09-25 08:00 | 2018-09-26 17:00 | 2018-09-25 08:00 | 2018-09-26 17:00 |  |  |  |  | 0d | 0d | 8 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 14 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 20:59 | 65 |  | 0 | 楍 |  |  |  | 1.2.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 19.2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.6 | [12 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.2.1.1 | 越早越好 |  |  | 0ed | 0d | 0d | 11 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-09-25 08:00 | 2018-09-25 08:48 | 2018-09-25 08:00 | 2018-09-25 08:48 | 2018-09-25 08:00 | 2018-09-25 08:48 |  |  |  |  | 0d | 0d | 8 | 12 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 15 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:14 | 65 | 16 | 0 | 楍 |  |  |  | 1.2.1.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.1.6 | 1.2.1.2 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
15.2h | 0h | 0h | 15.2h | 15.2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 可行性分析文档完成 |  | 1.2.1.2 | 越早越好 |  |  | 0ed | 0d | 0d | 12 |  | 500 |  | 0d | 0d | 1.9d | 1.9d | 1.9d | 0% | 0% | 2018-09-25 08:48 | 2018-09-26 17:00 | 2018-09-25 08:48 | 2018-09-26 17:00 | 2018-09-25 08:48 | 2018-09-26 17:00 |  |  |  |  | 0d | 0d | 11 | 13,15,14 | 罗培城 | 罗 | 初步可行性分析文档，可行性文档中的图表 |  |  | 可行性分析文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 16 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:15 | 15 | 17,21,121 | 0 | 楍 |  |  |  | 1.2.1.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 15.2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.2.1.1 | 1.3,1.3.1.1,1.3.1 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
697.83h | 0h | 0h | 697.83h | 697.83h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目计划 |  | 1.3 | 越早越好 |  |  | 0ed | 0d | 0d | 13 | 楍 | 500 |  | 0d | 0d | 37d | 37d | 37d | 0% | 0% | 2018-09-26 08:00 | 2018-11-14 17:00 | 2018-09-26 08:00 | 2018-11-14 17:00 | 2018-09-26 08:00 | 2018-11-14 17:00 |  |  |  |  | 0d | 0d | 12 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 2 | 17 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 21:16 | 16 |  | 0 | 楍 |  |  |  | 1.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 697.83h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.2.1.2 | [12 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
33.6h | 0h | 0h | 33.6h | 33.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求工程阶段-初步 |  | 1.3.1 | 越早越好 |  |  | 0ed | 0d | 0d | 14 | 楍 | 500 |  | 0d | 0d | 4d | 4d | 4d | 0% | 0% | 2018-09-26 08:00 | 2018-09-29 17:00 | 2018-09-26 08:00 | 2018-09-29 17:00 | 2018-09-26 08:00 | 2018-09-29 17:00 |  |  |  |  | 0d | 0d | 12 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 121 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 19:53 | 16 |  | 0 | 楍 |  |  |  | 1.3.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 33.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.2.1.2 | [12 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.1.1 | 越早越好 |  | 楍 | 0ed | 0d | 0.6d | 15 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-09-26 08:00 | 2018-09-26 08:48 | 2018-09-26 08:00 | 2018-09-26 08:48 | 2018-09-26 13:48 | 2018-09-26 14:36 |  |  |  |  | 0d | 0d | 12 | 16 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 21 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:29 | 16 | 114 | 0 | 楍 |  |  |  | 1.3.1.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.2.1.2 | 1.3.1.2 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求工程起草 |  | 1.3.1.2 | 越早越好 |  | 楍 | 0ed | 0.6d | 0.6d | 16 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-09-26 08:48 | 2018-09-26 11:12 | 2018-09-26 08:48 | 2018-09-26 11:12 | 2018-09-26 14:36 | 2018-09-27 08:00 |  |  |  |  | 0d | 0d | 15 | 17 | 张嘉诚 | 张 | 会议记录 |  |  | 需求工程起草文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 114 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 19:30 | 21 | 20 | 0 | 楍 |  |  |  | 1.3.1.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.1 | 1.3.1.3 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 甘特图 |  | 1.3.1.3 | 越早越好 |  |  | 0ed | 0d | 0d | 17 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-09-27 08:00 | 2018-09-27 17:00 | 2018-09-27 08:00 | 2018-09-27 17:00 | 2018-09-27 08:00 | 2018-09-28 08:00 |  |  |  |  | 0d | 0d | 16 | 18 | 郑丞钧 | 郑 | 会议记录 |  |  | 甘特图 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 20 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:28 | 114 | 18 | 0 | 楍 |  |  |  | 1.3.1.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.2 | 1.3.1.4 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | OBS |  | 1.3.1.4 | 越早越好 |  |  | 0ed | 0d | 0d | 18 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-09-28 08:00 | 2018-09-28 12:00 | 2018-09-28 08:00 | 2018-09-28 12:00 | 2018-09-28 08:00 | 2018-09-28 13:00 |  |  |  |  | 0d | 0d | 17 | 19 | 苏碧青 | 苏 | 甘特图 |  |  | OBS | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 18 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:24 | 20 | 19 | 0 | 楍 |  |  |  | 1.3.1.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.3 | 1.3.1.5 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | WBS |  | 1.3.1.5 | 越早越好 |  |  | 0ed | 0d | 0d | 19 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-09-28 13:00 | 2018-09-28 17:00 | 2018-09-28 13:00 | 2018-09-28 17:00 | 2018-09-28 13:00 | 2018-09-29 08:00 |  |  |  |  | 0d | 0d | 18 | 20 | 苏碧青 | 苏 | 甘特图 |  |  | WBS | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 19 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:26 | 18 | 116 | 0 | 楍 |  |  |  | 1.3.1.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.4 | 1.3.1.6 | [11 empty] | 延迟 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目章程 |  | 1.3.1.6 | 越早越好 |  |  | 0ed | 0d | 0d | 20 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-09-29 08:00 | 2018-09-29 09:36 | 2018-09-29 08:00 | 2018-09-29 09:36 | 2018-09-29 08:00 | 2018-09-29 09:36 |  |  |  |  | 0d | 0d | 19 | 21 | 赵豪杰 | 赵 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 116 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 19:40 | 19 | 22 | 0 | 楍 |  |  |  | 1.3.1.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.5 | 1.3.1.7 | [11 empty] | 按时 | 0% | 0% | 0% | Project Default (标准)
9.6h | 0h | 0h | 9.6h | 9.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目计划起草 |  | 1.3.1.7 | 越早越好 |  |  | 0ed | 0d | 0d | 21 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-09-29 08:00 | 2018-09-29 10:24 | 2018-09-29 08:00 | 2018-09-29 10:24 | 2018-09-29 08:00 | 2018-09-30 08:00 |  |  |  |  | 0d | 0d | 20 | 22,23 | 罗培城,苏碧青,张嘉诚,郑丞钧 | 罗,苏,张,郑 | OBS、WBS |  |  | 项目计划原型 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 22 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:31 | 116 | 122115 | 0 | 楍 |  |  |  | 1.3.1.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 9.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.6 | 1.3.2,1.3.2.1 | [11 empty] | 按时 | 0% | 0% | 0% | Project Default (标准)
24h | 0h | 0h | 24h | 24h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求工程阶段-修订 |  | 1.3.2 | 越早越好 |  |  | 0ed | 0d | 0d | 22 | 楍 | 500 |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2018-09-29 08:00 | 2018-09-30 17:00 | 2018-09-29 08:00 | 2018-09-30 17:00 | 2018-09-30 08:00 | 2018-09-30 17:00 |  |  |  |  | 0d | 0d | 21 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 122 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 19:55 | 22 |  | 0 | 楍 |  |  |  | 1.3.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 24h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.7 | [12 empty] | 按时 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求工程起草文档修订 |  | 1.3.2.1 | 越早越好 |  | 楍 | 0ed | 0d | 4.5d | 23 |  | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-09-30 08:00 | 2018-09-30 12:00 | 2018-09-30 08:00 | 2018-09-30 12:00 | 2018-10-05 08:00 | 2018-10-05 13:00 |  |  |  |  | 0d | 0d | 21 | 24 | 张嘉诚 | 张 | 需求工程起草文档 |  |  | 需求工程文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 115 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 19:30 | 22 | 23 | 0 | 楍 |  |  |  | 1.3.2.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.1.7 | 1.3.2.2 | [11 empty] | 按时 | 0% | 0% | 0% | Project Default (标准)
20h | 0h | 0h | 20h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目计划修订 |  | 1.3.2.2 | 越早越好 |  | 楍 | 0ed | 5d | 5d | 24 |  | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-09-30 08:00 | 2018-09-30 12:00 | 2018-09-30 08:00 | 2018-09-30 12:00 | 2018-10-05 13:00 | 2018-10-08 08:00 |  |  |  |  | 0d | 0d | 23 | 25,26 | 苏碧青,张嘉诚,赵豪杰,郑丞钧,罗培城 | 苏,张,赵,郑,罗 | 项目计划原型 |  |  | 项目计划 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 23 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 21:32 | 115 | 25,26 | 0 | 楍 |  |  |  | 1.3.2.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.2.1 | 1.3.3,1.3.3.1 | [11 empty] | 按时 | 0% | 0% | 0% | Project Default (标准)
125.83h | 0h | 0h | 125.83h | 125.83h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求获取 |  | 1.3.3 | 越早越好 |  |  | 0ed | 0d | 0d | 25 |  | 500 |  | 0d | 0d | 9d | 9d | 9d | 0% | 0% | 2018-10-08 08:00 | 2018-10-18 17:00 | 2018-10-08 08:00 | 2018-10-18 17:00 | 2018-10-08 08:00 | 2018-10-18 17:00 |  |  |  |  | 0d | 0d | 24 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 25 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 22:02 | 23 |  | 0 | 楍 |  |  |  | 1.3.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 125.83h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.2.2 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
0.8h | 0h | 0h | 0.8h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 定义愿景和范围 |  | 1.3.3.1 | 越早越好 |  | 楍 | 0ed | 0.9d | 3.27d | 26 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-10-08 08:00 | 2018-10-08 08:48 | 2018-10-08 08:00 | 2018-10-08 08:48 | 2018-10-11 10:10 | 2018-10-11 10:58 |  |  |  |  | 0d | 0d | 24 | 27 | 赵豪杰 | 赵 | 项目计划 |  |  | 定义结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 26 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:10 | 23 | 28 | 0 | 楍 |  |  |  | 1.3.3.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.2.2 | 1.3.3.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
0.8h | 0h | 0h | 0.8h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定需求开发过程 |  | 1.3.3.2 | 越早越好 |  | 楍 | 0ed | 0.9d | 2.37d | 27 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-10-09 08:00 | 2018-10-09 08:48 | 2018-10-09 08:00 | 2018-10-09 08:48 | 2018-10-11 10:58 | 2018-10-11 11:46 |  |  |  |  | 0d | 0d | 26 | 28 | 赵豪杰 | 赵 | 定义结果 |  |  | 开发过程 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 28 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:17 | 26 | 29 | 0 | 楍 |  |  |  | 1.3.3.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.1 | 1.3.3.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 用户群分类 |  | 1.3.3.3 | 越早越好 |  | 楍 | 0ed | 0d | 1.47d | 28 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-10-10 08:00 | 2018-10-10 12:00 | 2018-10-10 08:00 | 2018-10-10 12:00 | 2018-10-11 11:46 | 2018-10-11 16:46 |  |  |  |  | 0d | 0d | 27 | 29 | 张嘉诚 | 张 | 软件使用目标 |  |  | 分类结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 29 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:18 | 28 | 30 | 0 | 楍 |  |  |  | 1.3.3.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.2 | 1.3.3.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.3.4 | 越早越好 |  | 楍 | 0ed | 0.8d | 1.97d | 29 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-10 08:00 | 2018-10-10 09:36 | 2018-10-10 08:00 | 2018-10-10 09:36 | 2018-10-11 16:46 | 2018-10-12 09:22 |  |  |  |  | 0d | 0d | 28 | 30 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 30 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:19 | 29 | 31 | 0 | 楍 |  |  |  | 1.3.3.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.3 | 1.3.3.5 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.03h | 0h | 0h | 1.03h | 1.03h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 选择产品代表 |  | 1.3.3.5 | 越早越好 |  | 楍 | 0ed | 0d | 1.17d | 30 | 楍 | 500 |  | 0d | 0d | 0.13d | 0.13d | 0.13d | 0% | 0% | 2018-10-11 08:00 | 2018-10-11 09:02 | 2018-10-11 08:00 | 2018-10-11 09:02 | 2018-10-12 09:22 | 2018-10-12 10:24 |  |  |  |  | 0d | 0d | 29 | 31 | 苏碧青 | 苏 | 会议记录 |  |  | 选择结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 31 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:20 | 30 | 32 | 0 | 楍 |  |  |  | 1.3.3.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.03h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.4 | 1.3.3.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 建立核心队伍 |  | 1.3.3.6 | 越早越好 |  | 楍 | 0ed | 0.8d | 1.3d | 31 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-11 08:00 | 2018-10-11 09:36 | 2018-10-11 08:00 | 2018-10-11 09:36 | 2018-10-12 10:24 | 2018-10-12 13:00 |  |  |  |  | 0d | 0d | 30 | 32 | 赵豪杰 | 赵 | 会议记录 |  |  | 核心队伍 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 32 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:21 | 31 | 33 | 0 | 楍 |  |  |  | 1.3.3.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.5 | 1.3.3.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行需求访谈 |  | 1.3.3.7 | 越早越好 |  | 楍 | 0ed | 0d | 0.5d | 32 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-12 08:00 | 2018-10-12 09:36 | 2018-10-12 08:00 | 2018-10-12 09:36 | 2018-10-12 13:00 | 2018-10-12 14:36 |  |  |  |  | 0d | 0d | 31 | 33 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 会议记录 |  |  | 访谈记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 33 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:23 | 32 | 34 | 0 | 楍 |  |  |  | 1.3.3.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.6 | 1.3.3.8 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定使用实例 |  | 1.3.3.8 | 越早越好 |  | 楍 | 0ed | 0d | 0.5d | 33 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-12 09:36 | 2018-10-12 11:12 | 2018-10-12 09:36 | 2018-10-12 11:12 | 2018-10-12 14:36 | 2018-10-12 16:12 |  |  |  |  | 0d | 0d | 32 | 34 | 郑丞钧 | 郑 | 会议记录 |  |  | 使用实例 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 34 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:24 | 33 | 35 | 0 | 楍 |  |  |  | 1.3.3.8 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.7 | 1.3.3.9 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
4h | 0h | 0h | 4h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.3.9 | 越早越好 |  | 楍 | 0ed | 0.5d | 0.5d | 34 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-10-12 11:12 | 2018-10-12 12:00 | 2018-10-12 11:12 | 2018-10-12 12:00 | 2018-10-12 16:12 | 2018-10-13 13:00 |  |  |  |  | 0d | 0d | 33 | 35 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 35 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:25 | 34 | 36 | 0 | 楍 |  |  |  | 1.3.3.9 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.8 | 1.3.3.10 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 分析用户工作流程 |  | 1.3.3.10 | 越早越好 |  | 楍 | 0ed | 0d | 0.5d | 35 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-13 08:00 | 2018-10-13 17:00 | 2018-10-13 08:00 | 2018-10-13 17:00 | 2018-10-13 13:00 | 2018-10-15 13:00 |  |  |  |  | 0d | 0d | 34 | 36 | 张嘉诚 | 张 | 用户工作流程 |  |  | 分析结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 36 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:26 | 35 | 37 | 0 | 楍 |  |  |  | 1.3.3.10 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.9 | 1.3.3.11 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定质量属性 |  | 1.3.3.11 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 36 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-10-14 08:00 | 2018-10-14 10:24 | 2018-10-14 08:00 | 2018-10-14 10:24 | 2018-10-15 13:00 | 2018-10-15 15:24 |  |  |  |  | 0d | 0d | 35 | 37 | 张嘉诚 | 张 | 确定质量属性 |  |  | 确定结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 37 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:26 | 36 | 38 | 0 | 楍 |  |  |  | 1.3.3.11 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.10 | 1.3.3.12 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 检查问题报告 |  | 1.3.3.12 | 越早越好 |  | 楍 | 0ed | 0.5d | 0.8d | 37 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-10-15 08:00 | 2018-10-15 12:00 | 2018-10-15 08:00 | 2018-10-15 12:00 | 2018-10-15 15:24 | 2018-10-16 10:24 |  |  |  |  | 0d | 0d | 36 | 38 | 罗培城,郑丞钧 | 罗,郑 | 检查问题报告 |  |  | 检查结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 38 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:27 | 37 | 39 | 0 | 楍 |  |  |  | 1.3.3.12 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城,郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.11 | 1.3.3.13 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求重用 |  | 1.3.3.13 | 越早越好 |  | 楍 | 0ed | 0d | 0.3d | 38 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-16 08:00 | 2018-10-16 09:36 | 2018-10-16 08:00 | 2018-10-16 09:36 | 2018-10-16 10:24 | 2018-10-16 13:00 |  |  |  |  | 0d | 0d | 37 | 39 | 张嘉诚 | 张 | 用户需求 |  |  | 确认结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 39 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:38 | 38 | 40 | 0 | 楍 |  |  |  | 1.3.3.13 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.12 | 1.3.3.14 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
20h | 0h | 0h | 20h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.3.14 | 越早越好 |  | 楍 | 0ed | 0.5d | 0.5d | 39 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-10-16 08:00 | 2018-10-16 12:00 | 2018-10-16 08:00 | 2018-10-16 12:00 | 2018-10-16 13:00 | 2018-10-17 08:00 |  |  |  |  | 0d | 0d | 38 | 40 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 学习笔记 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 40 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:39 | 39 | 41 | 0 | 楍 |  |  |  | 1.3.3.14 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.13 | 1.3.3.15 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行需求确认 |  | 1.3.3.15 | 越早越好 |  |  | 0ed | 0d | 0d | 40 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-17 08:00 | 2018-10-17 09:36 | 2018-10-17 08:00 | 2018-10-17 09:36 | 2018-10-17 08:00 | 2018-10-17 09:36 |  |  |  |  | 0d | 0d | 39 | 41 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 会议记录 |  |  | 与杨枨老师确认结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 41 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:39 | 40 | 43 | 0 | 楍 |  |  |  | 1.3.3.15 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.14 | 1.3.3.16 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.3.16 | 越早越好 |  |  | 0ed | 0d | 0d | 41 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-17 09:36 | 2018-10-17 11:12 | 2018-10-17 09:36 | 2018-10-17 11:12 | 2018-10-17 09:36 | 2018-10-17 11:12 |  |  |  |  | 0d | 0d | 40 | 42 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 与杨枨老师确认结果 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 43 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:45 | 41 | 44 | 0 | 楍 |  |  |  | 1.3.3.16 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.15 | 1.3.3.17 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求整理 |  | 1.3.3.17 | 越早越好 |  |  | 0ed | 0d | 0d | 42 |  | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-17 11:12 | 2018-10-18 11:12 | 2018-10-17 11:12 | 2018-10-18 11:12 | 2018-10-17 11:12 | 2018-10-18 11:12 |  |  |  |  | 0d | 0d | 41 | 43,44 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 44 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:47 | 43 | 42,45 | 0 | 楍 |  |  |  | 1.3.3.17 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.16 | 1.3.4,1.3.4.1 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
176h | 0h | 0h | 176h | 176h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求分析 |  | 1.3.4 | 越早越好 |  |  | 0ed | 0d | 0d | 43 |  | 500 |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2018-10-18 11:12 | 2018-10-29 11:12 | 2018-10-18 11:12 | 2018-10-29 11:12 | 2018-10-18 11:12 | 2018-10-29 17:00 |  |  |  |  | 0d | 0d | 42 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 42 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-28 22:40 | 44 |  | 0 | 楍 |  |  |  | 1.3.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 176h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.17 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 绘制关联图 |  | 1.3.4.1 | 越早越好 |  |  | 0ed | 0d | 0d | 44 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-18 11:12 | 2018-10-19 11:12 | 2018-10-18 11:12 | 2018-10-19 11:12 | 2018-10-18 11:12 | 2018-10-19 11:12 |  |  |  |  | 0d | 0d | 42 | 45 | 苏碧青 | 苏 | 需求内容 |  |  | 关联图 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 45 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:50 | 44 | 46 | 0 | 楍 |  |  |  | 1.3.4.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.3.17 | 1.3.4.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 创建开发原型 |  | 1.3.4.2 | 越早越好 |  |  | 0ed | 0d | 0d | 45 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-19 11:12 | 2018-10-20 11:12 | 2018-10-19 11:12 | 2018-10-20 11:12 | 2018-10-19 11:12 | 2018-10-22 08:00 |  |  |  |  | 0d | 0d | 44 | 46 | 郑丞钧 | 郑 | 关联图 |  |  | 需求原型 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 46 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:51 | 45 | 47 | 0 | 楍 |  |  |  | 1.3.4.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.1 | 1.3.4.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 分析可行性 |  | 1.3.4.3 | 越早越好 |  |  | 0ed | 0d | 0d | 46 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-22 08:00 | 2018-10-22 17:00 | 2018-10-22 08:00 | 2018-10-22 17:00 | 2018-10-22 08:00 | 2018-10-23 08:00 |  |  |  |  | 0d | 0d | 45 | 47 | 罗培城 | 罗 | 需求原型 |  |  | 可行性分析文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 47 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:51 | 46 | 48 | 0 | 楍 |  |  |  | 1.3.4.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.2 | 1.3.4.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
0.8h | 0h | 0h | 0.8h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定需求优先级 |  | 1.3.4.4 | 越早越好 |  |  | 0ed | 0d | 0d | 47 | 楍 | 500 |  | 0d | 0d | 0.1d | 0.1d | 0.1d | 0% | 0% | 2018-10-23 08:00 | 2018-10-23 08:48 | 2018-10-23 08:00 | 2018-10-23 08:48 | 2018-10-23 08:00 | 2018-10-23 08:48 |  |  |  |  | 0d | 0d | 46 | 48 | 张嘉诚 | 张 | 可行性分析文档 |  |  | 需求优先级结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 48 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:52 | 47 | 49 | 0 | 楍 |  |  |  | 1.3.4.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 0.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.3 | 1.3.4.5 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 为需求建立模型 |  | 1.3.4.5 | 越早越好 |  |  | 0ed | 0d | 0d | 48 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-23 08:48 | 2018-10-24 08:48 | 2018-10-23 08:48 | 2018-10-24 08:48 | 2018-10-23 08:48 | 2018-10-24 08:48 |  |  |  |  | 0d | 0d | 47 | 49 | 赵豪杰 | 赵 | 需求优先级结果 |  |  | 需求模型 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 49 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:54 | 48 | 50 | 0 | 楍 |  |  |  | 1.3.4.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.4 | 1.3.4.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
7.2h | 0h | 0h | 7.2h | 7.2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.4.6 | 越早越好 |  |  | 0ed | 0d | 0d | 49 | 楍 | 500 |  | 0d | 0d | 0.9d | 0.9d | 0.9d | 0% | 0% | 2018-10-24 08:48 | 2018-10-24 17:00 | 2018-10-24 08:48 | 2018-10-24 17:00 | 2018-10-24 08:48 | 2018-10-25 08:00 |  |  |  |  | 0d | 0d | 48 | 50 | 赵豪杰 | 赵 | 需求模型 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 50 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:55 | 49 | 51 | 0 | 楍 |  |  |  | 1.3.4.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 7.2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.5 | 1.3.4.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行需求访谈 |  | 1.3.4.7 | 越早越好 |  |  | 0ed | 0d | 0d | 50 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-25 08:00 | 2018-10-25 17:00 | 2018-10-25 08:00 | 2018-10-25 17:00 | 2018-10-25 08:00 | 2018-10-26 08:00 |  |  |  |  | 0d | 0d | 49 | 51 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 会议记录 |  |  | 访谈记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 51 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-28 22:56 | 50 | 55 | 0 | 楍 |  |  |  | 1.3.4.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.6 | 1.3.4.8 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | UML学习 |  | 1.3.4.8 | 越早越好 |  |  | 0ed | 0d | 0d | 51 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-26 08:00 | 2018-10-26 17:00 | 2018-10-26 08:00 | 2018-10-26 17:00 | 2018-10-26 08:00 | 2018-10-27 08:00 |  |  |  |  | 0d | 0d | 50 | 52 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 55 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 08:55 | 51 | 52 | 0 | 楍 |  |  |  | 1.3.4.8 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.7 | 1.3.4.9 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 编写数据字典 |  | 1.3.4.9 | 不得早于...开始 | 2018-10-27 08:00 |  | 0ed | 0d | 0d | 52 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-27 08:00 | 2018-10-27 17:00 | 2018-10-27 08:00 | 2018-10-27 17:00 | 2018-10-27 08:00 | 2018-10-28 08:00 |  |  |  |  | 0d | 0d | 51 | 53 | 张嘉诚 | 张 | 系统内容 |  |  | 数据字典 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 52 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 08:48 | 55 | 53 | 0 | 楍 |  |  |  | 1.3.4.9 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.8 | 1.3.4.10 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.4.10 | 越早越好 |  |  | 0ed | 0d | 0d | 53 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-28 08:00 | 2018-10-28 09:36 | 2018-10-28 08:00 | 2018-10-28 09:36 | 2018-10-28 08:00 | 2018-10-29 08:00 |  |  |  |  | 0d | 0d | 52 | 54 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 数据字典 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 53 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 08:49 | 52 | 57 | 0 | 楍 |  |  |  | 1.3.4.10 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.9 | 1.3.4.11 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | UML复习 |  | 1.3.4.11 | 越早越好 |  |  | 0ed | 0d | 0d | 54 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-29 08:00 | 2018-10-29 17:00 | 2018-10-29 08:00 | 2018-10-29 17:00 | 2018-10-29 08:00 | 2018-10-30 08:00 |  |  |  |  | 0d | 0d | 53 | 55,56 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 57 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 08:59 | 53 | 66,67 | 0 | 楍 |  |  |  | 1.3.4.11 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.10 | 1.3.5,1.3.5.1 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
258.4h | 0h | 0h | 258.4h | 258.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求规格说明 |  | 1.3.5 | 越早越好 |  |  | 0ed | 0d | 0d | 55 |  | 500 |  | 0d | 0d | 12d | 12d | 12d | 0% | 0% | 2018-10-30 08:00 | 2018-11-14 17:00 | 2018-10-30 08:00 | 2018-11-14 17:00 | 2018-10-30 08:00 | 2018-11-14 17:00 |  |  |  |  | 0d | 0d | 54 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 66 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 09:02 | 57 |  | 0 | 楍 |  |  |  | 1.3.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 258.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.11 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.5.1 | 越早越好 |  |  | 0ed | 0d | 0d | 56 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-10-30 08:00 | 2018-10-30 09:36 | 2018-10-30 08:00 | 2018-10-30 09:36 | 2018-10-30 08:00 | 2018-10-30 09:36 |  |  |  |  | 0d | 0d | 54 | 57 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 需求分析文档 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 67 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:04 | 57 | 68 | 0 | 楍 |  |  |  | 1.3.5.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.4.11 | 1.3.5.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
12h | 0h | 0h | 12h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行访谈 |  | 1.3.5.2 | 越早越好 |  |  | 0ed | 0d | 0d | 57 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-10-30 09:36 | 2018-10-30 12:00 | 2018-10-30 09:36 | 2018-10-30 12:00 | 2018-10-30 09:36 | 2018-10-30 13:00 |  |  |  |  | 0d | 0d | 56 | 58 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 会议记录 |  |  | 访谈记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 68 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:07 | 67 | 69 | 0 | 楍 |  |  |  | 1.3.5.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.1 | 1.3.5.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 采用软件需求规格说明模板 |  | 1.3.5.3 | 越早越好 |  |  | 0ed | 0d | 0d | 58 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-10-30 13:00 | 2018-10-31 12:00 | 2018-10-30 13:00 | 2018-10-31 12:00 | 2018-10-30 13:00 | 2018-10-31 13:00 |  |  |  |  | 0d | 0d | 57 | 59 | 赵豪杰 | 赵 | 访谈记录 |  |  | 模板采用结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 69 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:08 | 68 | 70 | 0 | 楍 |  |  |  | 1.3.5.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.2 | 1.3.5.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
20h | 0h | 0h | 20h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.5.4 | 越早越好 |  |  | 0ed | 0d | 0d | 59 | 楍 | 500 |  | 0d | 0d | 0.5d | 0.5d | 0.5d | 0% | 0% | 2018-10-31 13:00 | 2018-10-31 17:00 | 2018-10-31 13:00 | 2018-10-31 17:00 | 2018-10-31 13:00 | 2018-11-01 08:00 |  |  |  |  | 0d | 0d | 58 | 60 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 模板采用结果 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 70 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:09 | 69 | 71 | 0 | 楍 |  |  |  | 1.3.5.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 20h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.3 | 1.3.5.5 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
16h | 0h | 0h | 16h | 16h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 指明需求来源 |  | 1.3.5.5 | 越早越好 |  |  | 0ed | 0d | 0d | 60 | 楍 | 500 |  | 0d | 0d | 2d | 2d | 2d | 0% | 0% | 2018-11-01 08:00 | 2018-11-02 17:00 | 2018-11-01 08:00 | 2018-11-02 17:00 | 2018-11-01 08:00 | 2018-11-03 15:24 |  |  |  |  | 0d | 0d | 59 | 61 | 郑丞钧 | 郑 | 需求记录 |  |  | 明确来源 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 71 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:09 | 70 | 72 | 0 | 楍 |  |  |  | 1.3.5.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 16h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.4 | 1.3.5.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
60h | 0h | 0h | 60h | 60h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 钓鱼用户访谈 |  | 1.3.5.6 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 61 | 楍 | 500 |  | 0d | 0d | 1.5d | 1.5d | 1.5d | 0% | 0% | 2018-11-03 08:00 | 2018-11-04 12:00 | 2018-11-03 08:00 | 2018-11-04 12:00 | 2018-11-03 15:24 | 2018-11-05 15:24 |  |  |  |  | 0d | 0d | 60 | 62 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 明确来源 |  |  | 访谈记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 72 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:10 | 71 | 73 | 0 | 楍 |  |  |  | 1.3.5.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 60h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 |  | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.5 | 1.3.5.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.5.7 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 62 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-05 08:00 | 2018-11-05 09:36 | 2018-11-05 08:00 | 2018-11-05 09:36 | 2018-11-05 15:24 | 2018-11-06 08:00 |  |  |  |  | 0d | 0d | 61 | 63 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 访谈记录 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 73 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:11 | 72 | 74 | 0 | 楍 |  |  |  | 1.3.5.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.6 | 1.3.5.8 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 为每一项需求注上记号 |  | 1.3.5.8 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 63 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-05 09:36 | 2018-11-06 09:36 | 2018-11-05 09:36 | 2018-11-06 09:36 | 2018-11-06 08:00 | 2018-11-07 08:00 |  |  |  |  | 0d | 0d | 62 | 64 | 张嘉诚 | 张 | 会议记录 |  |  | 标识需求 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 74 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 09:12 | 73 | 76 | 0 | 楍 |  |  |  | 1.3.5.8 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.7 | 1.3.5.9 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | UML学习 |  | 1.3.5.9 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 64 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-06 09:36 | 2018-11-07 09:36 | 2018-11-06 09:36 | 2018-11-07 09:36 | 2018-11-07 08:00 | 2018-11-08 08:00 |  |  |  |  | 0d | 0d | 63 | 65 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 76 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:44 | 74 | 75 | 0 | 楍 |  |  |  | 1.3.5.9 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.8 | 1.3.5.10 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 记录业务规范 |  | 1.3.5.10 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 65 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-07 09:36 | 2018-11-07 12:00 | 2018-11-07 09:36 | 2018-11-07 12:00 | 2018-11-08 08:00 | 2018-11-08 10:24 |  |  |  |  | 0d | 0d | 64 | 66 | 苏碧青 | 苏 | 项目需求 |  |  | 业务规范 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 75 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:44 | 76 | 80 | 0 | 楍 |  |  |  | 1.3.5.10 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.9 | 1.3.5.11 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | UML复习 |  | 1.3.5.11 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 66 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-07 13:00 | 2018-11-08 12:00 | 2018-11-07 13:00 | 2018-11-08 12:00 | 2018-11-08 10:24 | 2018-11-09 10:24 |  |  |  |  | 0d | 0d | 65 | 67 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 80 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:47 | 75 | 77 | 0 | 楍 |  |  |  | 1.3.5.11 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.10 | 1.3.5.12 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.5.12 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 67 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-08 13:00 | 2018-11-08 14:36 | 2018-11-08 13:00 | 2018-11-08 14:36 | 2018-11-09 10:24 | 2018-11-09 13:00 |  |  |  |  | 0d | 0d | 66 | 68 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 业务规范 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 77 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:46 | 80 | 78 | 0 | 楍 |  |  |  | 1.3.5.12 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.11 | 1.3.5.13 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 整理成需求规格说明书 |  | 1.3.5.13 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 68 |  | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-08 14:36 | 2018-11-09 14:36 | 2018-11-08 14:36 | 2018-11-09 14:36 | 2018-11-09 13:00 | 2018-11-12 13:00 |  |  |  |  | 0d | 0d | 67 | 69 | 赵豪杰 | 赵 | 会议记录 |  |  | 需求规格说明书 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 78 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:46 | 77 | 81 | 0 | 楍 |  |  |  | 1.3.5.13 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.12 | 1.3.5.14 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
12h | 0h | 0h | 12h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行交流 |  | 1.3.5.14 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 69 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-09 14:36 | 2018-11-09 17:00 | 2018-11-09 14:36 | 2018-11-09 17:00 | 2018-11-12 13:00 | 2018-11-12 15:24 |  |  |  |  | 0d | 0d | 68 | 70 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 需求规格说明书 |  |  | 交流记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 81 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 11:49 | 78 | 83 | 0 | 楍 |  |  |  | 1.3.5.14 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.13 | 1.3.5.15 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.3.5.15 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 70 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-12 08:00 | 2018-11-12 09:36 | 2018-11-12 08:00 | 2018-11-12 09:36 | 2018-11-12 15:24 | 2018-11-13 08:00 |  |  |  |  | 0d | 0d | 69 | 71 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 交流记录 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 83 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:04 | 81 | 84 | 0 | 楍 |  |  |  | 1.3.5.15 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.14 | 1.3.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 管理员访谈 |  | 1.3.6 | 越早越好 |  | 楍 | 0ed | 0d | 0.8d | 71 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-12 09:36 | 2018-11-13 09:36 | 2018-11-12 09:36 | 2018-11-13 09:36 | 2018-11-13 08:00 | 2018-11-14 08:00 |  |  |  |  | 0d | 0d | 70 | 72 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 84 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:04 | 83 | 85 | 0 | 楍 |  |  |  | 1.3.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.5.15 | 1.3.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 召开应用供需开发联系会议 |  | 1.3.7 | 越早越好 |  | 楍 | 0ed | 0.8d | 0.8d | 72 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-13 09:36 | 2018-11-14 09:36 | 2018-11-13 09:36 | 2018-11-14 09:36 | 2018-11-14 08:00 | 2018-11-15 08:00 |  |  |  |  | 0d | 0d | 71 | 73,74,75 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 85 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:05 | 84 | 118,86,87 | 0 | 楍 |  |  |  | 1.3.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.6 | 1.4,1.4.1,1.4.1.1 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
114h | 0h | 0h | 114h | 114h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目控制 |  | 1.4 | 越早越好 |  |  | 0ed | 0d | 0d | 73 | 楍 | 500 |  | 0d | 0d | 21d | 21d | 21d | 0% | 0% | 2018-11-15 08:00 | 2018-12-13 17:00 | 2018-11-15 08:00 | 2018-12-13 17:00 | 2018-11-15 08:00 | 2018-12-13 17:00 |  |  |  |  | 0d | 0d | 72 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 2 | 118 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 19:43 | 85 |  | 0 | 楍 |  |  |  | 1.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 114h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.7 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
56.8h | 0h | 0h | 56.8h | 56.8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求规格审核 |  | 1.4.1 | 越早越好 |  |  | 0ed | 0d | 0d | 74 |  | 500 |  | 0d | 0d | 8d | 8d | 8d | 0% | 0% | 2018-11-15 08:00 | 2018-11-26 17:00 | 2018-11-15 08:00 | 2018-11-26 17:00 | 2018-11-15 08:00 | 2018-11-26 17:00 |  |  |  |  | 0d | 0d | 72 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 86 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 12:06 | 85 |  | 0 | 楍 |  |  |  | 1.4.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 56.8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.7 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 审查需求文档 |  | 1.4.1.1 | 越早越好 |  | 楍 | 0ed | 0.7d | 3.5d | 75 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-15 08:00 | 2018-11-15 10:24 | 2018-11-15 08:00 | 2018-11-15 10:24 | 2018-11-20 13:00 | 2018-11-20 15:24 |  |  |  |  | 0d | 0d | 72 | 76 | 赵豪杰 | 赵 | 需求规格说明书 |  |  | 审查结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 87 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:07 | 85 | 88 | 0 | 楍 |  |  |  | 1.4.1.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.3.7 | 1.4.1.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.4.1.2 | 越早越好 |  | 楍 | 0ed | 0.8d | 2.8d | 76 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-16 08:00 | 2018-11-16 09:36 | 2018-11-16 08:00 | 2018-11-16 09:36 | 2018-11-20 15:24 | 2018-11-21 08:00 |  |  |  |  | 0d | 0d | 75 | 77 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 审查结果 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 88 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:07 | 87 | 89 | 0 | 楍 |  |  |  | 1.4.1.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.1 | 1.4.1.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 编写需求文档 |  | 1.4.1.3 | 越早越好 |  | 楍 | 0ed | 0d | 2d | 77 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-19 08:00 | 2018-11-19 17:00 | 2018-11-19 08:00 | 2018-11-19 17:00 | 2018-11-21 08:00 | 2018-11-22 08:00 |  |  |  |  | 0d | 0d | 76 | 78 | 罗培城 | 罗 | 会议记录 |  |  | 需求文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 89 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 12:08 | 88 | 90 | 0 | 楍 |  |  |  | 1.4.1.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.2 | 1.4.1.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 编写用户手册 |  | 1.4.1.4 | 越早越好 |  | 楍 | 0ed | 0d | 2d | 78 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-11-20 08:00 | 2018-11-20 17:00 | 2018-11-20 08:00 | 2018-11-20 17:00 | 2018-11-22 08:00 | 2018-11-23 08:00 |  |  |  |  | 0d | 0d | 77 | 79 | 苏碧青 | 苏 | 需求文档 |  |  | 用户手册 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 90 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 13:13 | 89 | 91 | 0 | 楍 |  |  |  | 1.4.1.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.3 | 1.4.1.5 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定合格的标准 |  | 1.4.1.5 | 越早越好 |  | 楍 | 0ed | 0.7d | 2d | 79 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-21 08:00 | 2018-11-21 10:24 | 2018-11-21 08:00 | 2018-11-21 10:24 | 2018-11-23 08:00 | 2018-11-23 10:24 |  |  |  |  | 0d | 0d | 78 | 80 | 张嘉诚 | 张 | 用户手册 |  |  | 合格标准 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 91 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 13:14 | 90 | 92 | 0 | 楍 |  |  |  | 1.4.1.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.4 | 1.4.1.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 管理员访谈 |  | 1.4.1.6 | 越早越好 |  | 楍 | 0ed | 0.8d | 1.3d | 80 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-22 08:00 | 2018-11-22 09:36 | 2018-11-22 08:00 | 2018-11-22 09:36 | 2018-11-23 10:24 | 2018-11-23 13:00 |  |  |  |  | 0d | 0d | 79 | 81 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 合格标准 |  |  | 访谈记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 92 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 13:29 | 91 | 94 | 0 | 楍 |  |  |  | 1.4.1.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.5 | 1.4.1.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.4.1.7 | 越早越好 |  | 楍 | 0ed | 0d | 0.5d | 81 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-23 08:00 | 2018-11-23 09:36 | 2018-11-23 08:00 | 2018-11-23 09:36 | 2018-11-23 13:00 | 2018-11-23 14:36 |  |  |  |  | 0d | 0d | 80 | 82 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 访谈记录 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 94 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 13:33 | 92 | 95 | 0 | 楍 |  |  |  | 1.4.1.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.6 | 1.4.1.8 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
12h | 0h | 0h | 12h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 与杨枨老师进行交流 |  | 1.4.1.8 | 越早越好 |  | 楍 | 0ed | 0.5d | 0.5d | 82 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-23 09:36 | 2018-11-23 12:00 | 2018-11-23 09:36 | 2018-11-23 12:00 | 2018-11-23 14:36 | 2018-11-26 08:00 |  |  |  |  | 0d | 0d | 81 | 83,84 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 会议记录 |  |  | 交流记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 95 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:38 | 94 | 97,98 | 0 | 楍 |  |  |  | 1.4.1.8 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 12h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.7 | 1.4.2,1.4.2.1 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
57.2h | 0h | 0h | 57.2h | 57.2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 需求管理 |  | 1.4.2 | 越早越好 |  |  | 0ed | 0d | 0d | 83 |  | 500 |  | 0d | 0d | 14d | 14d | 14d | 0% | 0% | 2018-11-26 08:00 | 2018-12-13 17:00 | 2018-11-26 08:00 | 2018-12-13 17:00 | 2018-11-26 08:00 | 2018-12-13 17:00 |  |  |  |  | 0d | 0d | 82 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 3 | 97 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 14:49 | 95 |  | 0 | 楍 |  |  |  | 1.4.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 57.2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.8 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.4.2.1 | 越早越好 |  | 楍 | 0ed | 0.8d | 15.45d | 84 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-26 08:00 | 2018-11-26 09:36 | 2018-11-26 08:00 | 2018-11-26 09:36 | 2018-12-17 11:36 | 2018-12-17 14:12 |  |  |  |  | 0d | 0d | 82 | 85 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 交流记录 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 98 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:51 | 95 | 99 | 0 | 楍 |  |  |  | 1.4.2.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.1.8 | 1.4.2.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2.4h | 0h | 0h | 2.4h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 确定变更控制过程 |  | 1.4.2.2 | 越早越好 |  | 楍 | 0ed | 0.7d | 14.65d | 85 | 楍 | 500 |  | 0d | 0d | 0.3d | 0.3d | 0.3d | 0% | 0% | 2018-11-27 08:00 | 2018-11-27 10:24 | 2018-11-27 08:00 | 2018-11-27 10:24 | 2018-12-17 14:12 | 2018-12-17 16:36 |  |  |  |  | 0d | 0d | 84 | 86 | 赵豪杰 | 赵 | 会议记录 |  |  | 变更控制过程 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 99 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:52 | 98 | 100 | 0 | 楍 |  |  |  | 1.4.2.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2.4h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.1 | 1.4.2.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 建立变更控制委员会 |  | 1.4.2.3 | 越早越好 |  | 楍 | 0ed | 0.8d | 13.95d | 86 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-28 08:00 | 2018-11-28 09:36 | 2018-11-28 08:00 | 2018-11-28 09:36 | 2018-12-17 16:36 | 2018-12-18 09:12 |  |  |  |  | 0d | 0d | 85 | 87 | 赵豪杰 | 赵 | 变更控制过程 |  |  | 变更控制委员会 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 100 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:54 | 99 | 101 | 0 | 楍 |  |  |  | 1.4.2.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.2 | 1.4.2.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 进行变更影响分析 |  | 1.4.2.4 | 越早越好 |  | 楍 | 0ed | 0.8d | 13.15d | 87 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-11-29 08:00 | 2018-11-29 09:36 | 2018-11-29 08:00 | 2018-11-29 09:36 | 2018-12-18 09:12 | 2018-12-18 10:48 |  |  |  |  | 0d | 0d | 86 | 88 | 罗培城 | 罗 | 变更控制委员会 |  |  | 变更影响分析 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 101 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:54 | 100 | 102 | 0 | 楍 |  |  |  | 1.4.2.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.3 | 1.4.2.5 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
2h | 0h | 0h | 2h | 2h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 跟踪每一项变更 |  | 1.4.2.5 | 越早越好 |  | 楍 | 0ed | 0.75d | 12.35d | 88 | 楍 | 500 |  | 0d | 0d | 0.25d | 0.25d | 0.25d | 0% | 0% | 2018-11-30 08:00 | 2018-11-30 10:00 | 2018-11-30 08:00 | 2018-11-30 10:00 | 2018-12-18 10:48 | 2018-12-18 13:48 |  |  |  |  | 0d | 0d | 87 | 89 | 郑丞钧 | 郑 | 变更影响分析 |  |  | 跟踪状态记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 102 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:56 | 101 | 103 | 0 | 楍 |  |  |  | 1.4.2.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 2h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.4 | 1.4.2.6 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
1.6h | 0h | 0h | 1.6h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 编写需求文档的基准版本和控制版本 |  | 1.4.2.6 | 越早越好 |  | 楍 | 0ed | 0.8d | 11.6d | 89 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-12-03 08:00 | 2018-12-03 09:36 | 2018-12-03 08:00 | 2018-12-03 09:36 | 2018-12-18 13:48 | 2018-12-18 15:24 |  |  |  |  | 0d | 0d | 88 | 90 | 苏碧青 | 苏 | 跟踪状态记录 |  |  | 需求文档基准版本和控制版本 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 103 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 14:57 | 102 | 104 | 0 | 楍 |  |  |  | 1.4.2.6 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 苏碧青 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 1.6h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.5 | 1.4.2.7 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 维护变更历史纪录 |  | 1.4.2.7 | 越早越好 |  | 楍 | 0ed | 0d | 10.8d | 90 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-04 08:00 | 2018-12-04 17:00 | 2018-12-04 08:00 | 2018-12-04 17:00 | 2018-12-18 15:24 | 2018-12-19 15:24 |  |  |  |  | 0d | 0d | 89 | 91 | 张嘉诚 | 张 | 需求文档基准版本和控制版本 |  |  | 维护结果 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 104 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 15:00 | 103 | 105 | 0 | 楍 |  |  |  | 1.4.2.7 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.6 | 1.4.2.8 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.4.2.8 | 越早越好 |  | 楍 | 0ed | 0.8d | 10.8d | 91 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-12-05 08:00 | 2018-12-05 09:36 | 2018-12-05 08:00 | 2018-12-05 09:36 | 2018-12-19 15:24 | 2018-12-20 08:00 |  |  |  |  | 0d | 0d | 90 | 92 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 维护结果 |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 105 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:09 | 104 | 106 | 0 | 楍 |  |  |  | 1.4.2.8 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.7 | 1.4.2.9 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 跟踪需求状态 |  | 1.4.2.9 | 越早越好 |  | 楍 | 0ed | 0d | 10d | 92 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-06 08:00 | 2018-12-06 17:00 | 2018-12-06 08:00 | 2018-12-06 17:00 | 2018-12-20 08:00 | 2018-12-21 08:00 |  |  |  |  | 0d | 0d | 91 | 93 | 赵豪杰 | 赵 | 会议记录 |  |  | 跟踪状态记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 106 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:10 | 105 | 107 | 0 | 楍 |  |  |  | 1.4.2.9 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.8 | 1.4.2.10 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 衡量需求稳定性 |  | 1.4.2.10 | 越早越好 |  | 楍 | 0ed | 0d | 10d | 93 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-07 08:00 | 2018-12-07 17:00 | 2018-12-07 08:00 | 2018-12-07 17:00 | 2018-12-21 08:00 | 2018-12-24 08:00 |  |  |  |  | 0d | 0d | 92 | 94 | 罗培城 | 罗 | 跟踪状态记录 |  |  | 需求稳定性记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 107 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:11 | 106 | 108 | 0 | 楍 |  |  |  | 1.4.2.10 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 罗培城 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.9 | 1.4.2.11 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 使用需求管理工具 |  | 1.4.2.11 | 越早越好 |  | 楍 | 0ed | 10d | 10d | 94 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-10 08:00 | 2018-12-10 17:00 | 2018-12-10 08:00 | 2018-12-10 17:00 | 2018-12-24 08:00 | 2018-12-25 08:00 |  |  |  |  | 0d | 0d | 93 | 95,96 | 郑丞钧 | 郑 | 需求稳定性记录 |  |  | 存储需求 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 4 | 108 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:13 | 107 | 109110 | 0 | 楍 |  |  |  | 1.4.2.11 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 郑丞钧 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.10 | 1.5,1.5.1 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
96h | 0h | 0h | 96h | 96h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 项目收尾 |  | 1.5 | 越早越好 |  |  | 0ed | 0d | 0d | 95 |  | 500 |  | 0d | 0d | 12d | 12d | 12d | 0% | 0% | 2018-12-25 08:00 | 2019-01-09 17:00 | 2018-12-25 08:00 | 2019-01-09 17:00 | 2018-12-25 08:00 | 2019-01-09 17:00 |  |  |  |  | 0d | 0d | 94 | [23 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | ￥0.00 | PRD2018-G06-GANTT | 2 | 109 | 0 | 0 | 0 | 0 | 0 |  | 2018-09-29 16:14 | 108 |  | 0 | 楍 |  |  |  | 1.5 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 |  |  | ￥0.00 | 固定工期 | 楍 | 楍 | 0h | 0h | 0h | 96h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.11 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 文档整理 |  | 1.5.1 | 越早越好 |  | 楍 | 0ed | 0d | 8.8d | 96 |  | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-25 08:00 | 2018-12-25 17:00 | 2018-12-25 08:00 | 2018-12-25 17:00 | 2019-01-04 15:24 | 2019-01-07 15:24 |  |  |  |  | 0d | 0d | 94 | 97 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | 需求规格说明书 |  |  | 项目文档 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 110 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:15 | 108 | 111 | 0 | 楍 |  |  |  | 1.5.1 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.4.2.11 | 1.5.2 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 制作PPT |  | 1.5.2 | 越早越好 |  | 楍 | 0ed | 0d | 8.8d | 97 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2018-12-26 08:00 | 2018-12-26 17:00 | 2018-12-26 08:00 | 2018-12-26 17:00 | 2019-01-07 15:24 | 2019-01-08 15:24 |  |  |  |  | 0d | 0d | 96 | 98 | 张嘉诚 | 张 | 需求稳定性记录 |  |  | ppt | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 111 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:15 | 110 | 112 | 0 | 楍 |  |  |  | 1.5.2 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 张嘉诚 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.5.1 | 1.5.3 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
8h | 0h | 0h | 8h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 小组会议 |  | 1.5.3 | 越早越好 |  | 楍 | 0ed | 8.8d | 8.8d | 98 | 楍 | 500 |  | 0d | 0d | 0.2d | 0.2d | 0.2d | 0% | 0% | 2018-12-27 08:00 | 2018-12-27 09:36 | 2018-12-27 08:00 | 2018-12-27 09:36 | 2019-01-08 15:24 | 2019-01-09 08:00 |  |  |  |  | 0d | 0d | 97 | 99 | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | ppt |  |  | 会议记录 | [16 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 112 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:16 | 111 | 113 | 0 | 楍 |  |  |  | 1.5.3 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 8h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.5.2 | 1.5.4 | [11 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)
40h | 0h | 0h | 40h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | 答辩 |  | 1.5.4 | 越早越好 |  |  | 0ed | 0d | 0d | 99 | 楍 | 500 |  | 0d | 0d | 1d | 1d | 1d | 0% | 0% | 2019-01-09 08:00 | 2019-01-09 17:00 | 2019-01-09 08:00 | 2019-01-09 17:00 | 2019-01-09 08:00 | 2019-01-09 17:00 |  |  |  |  | 0d | 0d | 98 |  | 罗培城,苏碧青,张嘉诚,赵豪杰,郑丞钧 | 罗,苏,张,赵,郑 | [20 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | ￥0.00 | PRD2018-G06-GANTT | 3 | 113 | 0 | 0 | 0 | 0 | 0 | 楍 | 2018-09-29 16:17 | 112 |  | 0 | 楍 |  |  |  | 1.5.4 | 0d | 0d | 0d | ￥0.00 | ￥0.00 | ￥0.00 | 楍 | 楍 | 楍 | 赵豪杰 |  | ￥0.00 | 固定单位 | 楍 | 楍 | 0h | 0h | 0h | 40h | ￥0.00 | ￥0.00 | ￥0.00 | 按比例 |  |  |  |  | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 |  | 楍 | Flat | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | ￥0.00 | [10 empty] | 0d | 0d | 0d | 0d | 0d | 0d | 0d | [10 empty] | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 楍 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | [20 empty] | 0d | 0% | A |  |  | 1.5.3 | [12 empty] | 将来任务 | 0% | 0% | 0% | Project Default (标准)